## Risk Register
RISK MGT ADMIN |  | STEP 1 |  |  | STEP 2 |  |  |  | STEP 1 | STEP 3 | S2 | STEP 3 | [5 empty] | RISK MGT ADMIN
Risk I.D. | Risk cat | Type I or R | Raised by | Date Raised | Likelihood | Impact | Gross Risk Exposure | Phasing or Proximity of impact | Description | Mitigation or other risk response | Owner | Target Date | Revised Likelihood | Revised Impact |  | Residual Risk Exposure | Current Perceived Trajectory | Status | Date last rev'd by board
EGS001 | 2 | R | BB | 2014-11-17 | 3 | 5 | 15 | !!! | # Agreement not reached on funding structure means that staff cannot be recruited and trained in time to deliver service from 07/09/15 | # Consult closely with the Programme Board (Senior Sponsor) and the Administrative Senior User through the Project Executive to reach a funding agreement in time to start the recruitment process by 18/05/15 | CC | 2015-05-18 | 3 | 5 | R | 15 | ▲ | O | 2015-03-26
EGS002 | 7 | R | BB | 2014-11-17 | 3 | 5 | 15 | !! | # eCSIS changes not completed by 28/06/15 prevent the agreed new processes being used when new service delivery model commences meaning benefits for exam committee processes not realised | # OBIS BP to ensure that required eCSIS changes are prioritized through the ELM Group and delivered by 28/6/15 # "To Be" processes from BPR to be reviewed by OBIS BP to give assurance no greater eCSIS amendments needed than anticipated | CC | 2015-06-28 | 1 | 4 | A | 4 | ▼ | T | 2015-03-26
[5 empty] | 1 | 4 | 4 | ! |  |  |  |  | 3 | 2 | Y | 6 | ► | M
FORMATTING DOES NOT EXTEND BEYOND THIS LINE: PLS REPLICATE ADDITIONAL ROWS FROM THOSE ABOVE
Note on C2: R = Risk; a potential situation/incident that may happen I = Issue; an actual situation/incident that has happened/exists
Note on D2: Enter initials or some means by which the individual that flagged-up this risk can be identified. WHY?: To ensure that best practice can be maintained and the person raising the risk is not responsible for assessing the risk or deciding the risk response.
Note on L2: This is the person a) best placed to effectively monitor the changes to the level of risk, and b) accountable for ensuring action takes place. It is not necessarily the person responsible for performing the action.
Note on M2: Date for risk response actions to be completed by
Note on Q2: The risk levels with existing controls and mitigating actions in place
Note on R2: This is an indication of whether horizon scanning suggests that overall the risk exposure is increasing, decreasing or stable. It is not a measure of success for the risk response as it should also take account of the effect of external or uncontrollable factors
Note on S2: O = Newly Open. No risk response yet agreed T = Risk tolerated/accepted by project board with no action required. M = Mitigation or other risk response agreed by Project Board E = Escalation to Programme Board or Corporate Portfolio Mgmt. agreed by Project Board C = Risk Closed by Project Board as time for event has passed

## Summary Report
Project Risk Profile Summary
Status of risks |  | Current Total | Residual risk score |  | Current Total
Open | O | 1 | Red |  | 1
Tolerated | T | 1 | Amber |  | 1
Mitigated | M | 1 | Yellow |  | 1
Escalated | E | 0 | Green |  | 0
Closed | C | 0
Phasing or Proximity |  | Current Total | Current trajectory of risk exposure |  | Current Total
Imminent | !!! | 1 | Increasing | ▲ | 1
Short-term | !! | 1 | Stable | ► | 1
Long-term | ! | 1 | Reducing | ▼ | 1

## Scoring Guide
“A risk event is an uncertain event or set of circumstances that, should it occur, |  |  | R
will have an effect on achievement of one or more of the project’s objectives” (APM PRAM Guide) |  |  | I
Risk Register Scoring Guidance |  |  | O
T
Likelihood (1, 2, 3, 4, 5) |  |  | M
Ø Identify the likelihood of the gross risk using the following table |  |  | E
Ø Likelihood – what is the likelihood of materially failing to achieve the objective / outcome? |  |  | C
Table 1 Risk Likelihood Framework: |  |  | !!!
!!
LIKELIHOOD | SCORE | DESCRIPTION | !
Very High | 5 | Almost certainly will occur
High | 4 | Probable. More likely to occur than not | ▲ | ↔ | ► | Ý
Medium | 3 | Fairly likely to occur | ► | ↑ | ▲ | Ü
Low | 2 | Unlikely but possibility could occur under some circumstances | ▼ | ↓ | ▼ | Þ
Very Low | 1 | Rare. Extremely unlikely. Would occur only in exceptional circumstances
84
Impact (1, 2, 3, 4, 5)
Ø Identify the impact of the gross risk using the following table |  |  | R | R | R | R | R
Ø Impact – If the risk transpires would be the impact on the stated deliverables and outcomes of your project? |  |  | A | A | R | R | R
|  |  | Y | Y | A | A | R
Table 2 Risk Impact Framework: |  |  | G | G | Y | A | A
|  |  | G | G | G | Y | A
PROJECT LEVEL IMPACT DEFINITIONS
5: CATASTROPHIC | • Would pose a serious threat to the project’s survival • Would prevent the achievement of project objectives • Would have very serious financial consequences not manageable within existing project resources• Would have a major impact at faculty/service level and/or a moderate impact at University level • Would necessitate very significant changes to the project plan, intended outcomes, and operational delivery • Would have a major impact compromising operational performance at faculty/service level and/or a moderate impact at University level • Would require major intervention at faculty/service level and/or moderate intervention at University level to resolve
4: MAJOR | • Would seriously hinder the achievement of project objectives • Would have serious financial consequences that may require significant reallocation of project resources • Would necessitate some changes to the project plan and/or intended outcomes • Would necessitate significant changes to project delivery • Would have a moderate impact on operational performance at faculty/service level and/or a minor impact at University level • Would require moderate intervention at faculty/service level and/or minor intervention at University level to resolve
3: MODERATE | • Would hinder the achievement of some project objectives • Would have financial consequences that could be managed by flexing existing project budget • May necessitate some changes to the project plan and/or intended outcomes • Would necessitate some changes to project delivery • Would have a minor impact or inconvenience at faculty/service level and/or an insignificant impact at University level • Would require minor intervention at faculty/service level and/or insignificant intervention at University level to resolve
2: MINOR | • Would hinder the achievement of some aspects of project objectives • Would have financial consequences that could be managed with existing project budget • May necessitate some changes to project delivery • Would have an insignificant impact at faculty/service level • Would require intervention by Project Sponsor or Programme Management only to resolve
1:INSIGINFICIANT | • Would have only a marginal effect on the achievement of some aspects of project objectives • Would have only marginal financial consequences • Would be managed with existing systems/procedures • No impact on operational performance of Faculty/Directorate • Would require Project Manager intervention only in order to resolve

## Response & Mgt Guide
Risk Register Response, Escalation and Management Guidance
5 - CATASTROPHIC |  |  |  | 5 |  |  | 10 |  |  | 15 |  |  | 20 |  |  | 25 |  | Guide to level of expected risk response actions | Escalation Rules
|  |  | 1/5 |  |  | 2/5 |  |  | 3/5 |  |  | 4/5 |  |  | 5/5
4 - MAJOR |  |  |  | 4 |  |  | 8 |  |  | 12 |  |  | 16 |  |  | 20 | RED | = Outside Appetite / Don’t Tolerate / Take Action to Reduce Risk / Consider stopping action or project to remove such high level of risk. | Mandatory escalation: # All red risks must be escalated to your Programme Board for approval of your Project Boards agreed risk response. # All red risks must be reviewed by your Project Board at every meeting to check for any perceived change in status and to closely monitor progress on response
|  |  | 1/4 |  |  | 2/4 |  |  | 3/4 |  |  | 4/4 |  |  | 5/4
I
3 - MODERATE |  |  |  | 3 |  |  | 6 |  |  | 9 |  |  | 12 |  |  | 15 | AMBER | = Outside Appetite / Don’t Tolerate / Take Action to Reduce Risk | Discretionary escalation: # Amber risks may be escalated to Programme Board, (or Executive Board if no overarching Programme Board exists) at the Project Executive/Sponsors discretion, or # if the risk may have impact beyond the deliverables of the project.
M
| P |  | 1/3 |  |  | 2/3 |  |  | 3/3 |  |  | 4/3 |  |  | 5/3
A
C
2 - MINOR | T |  |  | 2 |  |  | 4 |  |  | 6 |  |  | 8 |  |  | 10 | YELLOW | = Just outside Appetite / Consider Action to Reduce Risk | Normal escalation: Escalated to Programme Board, (or Executive Board if no overarching Programme Board exists) only if the risk may have impact beyond the deliverables of the project.
|  |  | 1/2 |  |  | 2/2 |  |  | 3/2 |  |  | 4/2 |  |  | 5/2
1 - INSIGNIFICANT |  |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 | GREEN | = Within Appetite / Tolerate
|  |  | 1/1 |  |  | 2/1 |  |  | 3/1 |  |  | 4/1 |  |  | 5/1
L I K E L I H O O D
|  | 1 - VERY LOW |  |  | 2 - LOW |  |  | 3 - MEDIUM |  |  | 4 - HIGH |  |  | 5 - VERY HIGH